## Project Timeline
SENTINEL AI — DevOps Incident Response Agent ¦ Project Timeline
Project Start: 25-Apr-2026 ¦ Duration: 10 working days ¦ Owner: Data Scientist (Personal Project)
Date | Features | Milestone | Milestone Description | Estimated Days | Hours Spent | % Completion
25-Apr-2026 (Sat) | Project Setup | Repository & Environment Initialization | Create GitHub repo, set up virtual environment, initialize folder structure (simulator/, agents/, memory/, api/, frontend/), create requirements.txt with FastAPI, LangGraph, ChromaDB, Pydantic; configure .env.example and .gitignore. | 0.5 | 1 | 100%
25-Apr-2026 (Sat) | Simulated Environment - Services | Microservice Definitions Built | Define 5 simulated microservices (api-gateway, auth-service, order-service, payment-service, postgres-db) with their roles, dependencies, and baseline behavior in services.py. | 0.5 | 2 | 100%
26-Apr-2026 (Sun) | Simulated Environment - Generators | Realistic Log & Metric Generators Working | Build log_generator.py producing timestamped logs with service names, log levels, and stack traces. Build metric_generator.py producing CPU%, memory%, request latency, and error rate streams that evolve over time. | 1 | 6 | 100%
10-May-2026 (Sun) | Incident Scenarios | First 3 Incident Scenarios Implemented | Implement DB connection pool exhaustion, memory leak in auth-service, and cascading failure scenarios in incidents.py with realistic symptom evolution. Add incident_injector to trigger them on demand. | 1 | 1 | 100%
10-May-2026 (Sun) | LangGraph Orchestrator | Agent Pipeline State Machine Operational | Set up LangGraph orchestrator.py with the full state machine (Monitoring → Diagnosis → Remediation → Verification → Post-Mortem). Define shared state schema and transition logic between agent nodes. | 1 | 2 | 80%
28-Apr-2026 (Tue) | Monitor Agent | Anomaly Detection Agent Live | Implement Monitor Agent with rule-based thresholds (CPU > 85%, memory > 90%, error rate > 5%, latency p99 > 2s) plus LLM-based pattern matching for unusual log sequences. Output structured alerts. | 1 | 4 | 90%
29-Apr-2026 (Wed) | Diagnosis Agent | ReAct-based Root Cause Analysis Working | Implement Diagnosis Agent with ReAct pattern. Define tools: get_service_logs, get_service_metrics, get_service_dependencies, query_incident_memory, get_recent_deployments. Output root cause with confidence score and evidence chain. | 1 | 3 | 80%
29-Apr-2026 (Wed) | Remediation Agent | Safety-Classified Remediation Engine | Implement Remediation Agent with action tools (restart_service, scale_service, rollback_deployment, flush_connection_pool, update_rate_limit, clear_cache). Add 3-tier safety classification (low/medium/high risk) and human-in-the-loop approval flow for high-risk actions. | 1 | 2 | 80%
30-Apr-2026 (Thu) | ChromaDB Memory System | Vector-based Incident Memory Online | Build incident_memory.py using ChromaDB. Implement embedding storage with schema {incident_type, symptoms, root_cause, resolution, timestamp}. Add similarity search so Diagnosis Agent can recall past incidents. | 0.5 | 4 | 100%
30-Apr-2026 (Thu) | Post-Mortem Agent | Automated Incident Reports Generated | Implement Post-Mortem Agent that generates structured reports (timeline, root cause, actions taken, impact, prevention recommendations) and writes learnings into the memory system. | 0.5 | 3 | 100%
01-May-2026 (Fri) | FastAPI Backend & WebSocket | Real-Time Backend API Operational | Build FastAPI app in main.py with REST routes (api/routes.py) for triggering incidents and fetching state, plus WebSocket server (api/websocket.py) for streaming logs, metrics, and agent state to the frontend. | 1 | 1 | 50%
02-May-2026 (Sat) | Dashboard Frontend Layout | 4-Panel Command Center UI Built | Build single-page dashboard (index.html, style.css) with dark theme (#0a0a1a), neon accents, glassmorphism panels, and 4-panel layout: Metrics, Agent Workflow, Log Stream, Incident Timeline. Use Inter + JetBrains Mono fonts. | 1 |  | 0%
03-May-2026 (Sun) | Real-Time Visualizations | Live Charts, Logs & Agent Visualizer | Implement charts.js (Chart.js metrics with CPU/MEM/LAT/ERR), agent-visualizer.js (live agent workflow nodes that glow when active), log-viewer.js (scrolling log stream), and incident trigger panel. Wire everything to WebSocket via websocket.js. | 1 |  | 0%
04-May-2026 (Mon) | Testing & Validation | End-to-End Test Suite Passing | Write pytest tests for simulator (test_simulator.py) and agents (test_agents.py). Run end-to-end tests for all incident scenarios. Verify each scenario completes detection → diagnosis → remediation cycle in < 60 seconds. | 0.3 |  | 0%
04-May-2026 (Mon) | Containerization & Deployment | Application Deployed to Render | Write Dockerfile, build and test container locally, push to GitHub, deploy to Render. Verify production deployment renders dashboard correctly and handles incident triggers without lag. | 0.4 |  | 0%
04-May-2026 (Mon) | Documentation & Demo | Project Ready for Portfolio | Write comprehensive README with architecture diagram, setup steps, demo GIFs, and live link. Record 60-second demo video showing full incident-to-resolution flow. Clean up code, add docstrings, finalize for GitHub showcase. | 0.3 |  | 0%
TOTAL | 16 milestones across 5 phases |  |  | 12 | 29 | 61.25%

## Phase Summary
Phase-Level Summary
Phase | Focus Area | Estimated Days | Actual Days | % Completion
Phase 1 | Foundation — Simulated environment & incidents | 3 |  | 0%
Phase 2 | Agent Core — Monitor, Diagnosis, Remediation | 4 |  | 0%
Phase 3 | Memory & Intelligence — ChromaDB + Post-Mortem | 1 |  | 0%
Phase 4 | Dashboard — Real-time WebSocket UI | 3 |  | 0%
Phase 5 | Polish & Deploy — Testing, Docker, Render | 1 |  | 0%
TOTAL | Full project | 12 | 0 | 0%